## Summary
Gate checklists — status across the five gates
Counts read from each gate sheet. Nothing to fill in here.
Gate | What it decides | Criteria met | Not met | Not applicable
G1 | Qualification and provisional risk
G2 | Architecture and data readiness
G3 | Deployment authorization
G4 | Material change
G5 | Retirement
Run the entry list before the meeting, not in it. A gate whose first twenty minutes are spent establishing whether the evidence exists is a status meeting.

## G1
G1 — Qualification and provisional risk
Entry criteria, expanded into what each one means in practice.
Set Status to Met, Not met or Not applicable. A completed checklist is not evidence — the evidence is the record it told you to complete.
# | Criterion | Usual owner | Status | Evidence — where the record lives | Date | Note
1 | Named capability or stakeholder need, with a current and a target measure | Sponsor
2 | Expected outcome stated as a measure with a baseline you can read today | Sponsor
3 | Named business sponsor with the authority to stop the work | Sponsor
4 | The non-AI alternative considered, and the rejection recorded | Sponsor
5 | Decision or action the output supports, written in one sentence | Architect
6 | Affected parties listed, including people who will never use the system | Architect
7 | Intended autonomy at launch, in the words of a D2 anchor | Architect
8 | Provisional D1–D5 present and marked provisional | Risk Lead
9 | Data path identified in principle, with a sensitivity signal | Data Owner
10 | No architecture or vendor commitment embedded in the canvas | Architect
11 | Regulatory or contractual constraints from the sector overlay noted | Risk Lead
Criteria met
Outstanding, and blocking
Gate decision: approve / approve with conditions / remediate / escalate / reject
Decision, decided by, and date

## G2
G2 — Architecture and data readiness
Entry criteria, expanded into what each one means in practice.
Set Status to Met, Not met or Not applicable. A completed checklist is not evidence — the evidence is the record it told you to complete.
# | Criterion | Usual owner | Status | Evidence — where the record lives | Date | Note
1 | ADR complete: model, hosting, grounding and boundary named in comparable form | Architect
2 | Alternatives considered, with the reason each was rejected | Architect
3 | Pattern conformance assessed: conformant, modified with detail, or novel | Architect
4 | Failure behaviour stated: model unavailable, slow, or wrong | Architect
5 | Lineage record complete, every source named and owned | Data Owner
6 | Every grounding source has a refresh cadence and a maximum staleness | Data Owner
7 | Derived stores listed: indexes, embeddings, caches, evaluation sets | Data Owner
8 | Risk score revisited against the now-known architecture; tier confirmed | Risk Lead
9 | Effective-autonomy threshold agreed now, before anyone knows the number | Risk Lead
10 | Vendor due diligence complete, or the tier capped, or acceptance recorded | Architect
11 | Agentic systems: authority boundary drafted in the enforcement point's language | Security Architect
12 | Concentration checked at Tier 3–4: what else depends on this supplier | Architect
Criteria met
Outstanding, and blocking
Gate decision: approve / approve with conditions / remediate / escalate / reject
Decision, decided by, and date

## G3
G3 — Deployment authorization
Entry criteria, expanded into what each one means in practice.
Set Status to Met, Not met or Not applicable. A completed checklist is not evidence — the evidence is the record it told you to complete.
# | Criterion | Usual owner | Status | Evidence — where the record lives | Date | Note
1 | Evaluation complete, with pass criteria defined before the run | System Owner
2 | Assurance summary at the depth the tier requires, including what was not tested | System Owner
3 | Directional error rates reported separately where errors are asymmetric | System Owner
4 | Control matrix complete: each control mapped to a specific risk, each emitting evidence | Risk Lead
5 | Named accountable owner recorded — a person, not a function | AI Governance Lead
6 | Human oversight point confirmed at Tier 2+, with the time budget stated | System Owner
7 | Authorized configuration written as data: version, sources, action surface, environment | Architect
8 | Machine-readable permission boundary in place for agentic systems | Security Architect
9 | Kill-switch conditions defined and separately approved at Tier 3–4 | AI Governance Body
10 | Monitoring commitments agreed: which signals, what thresholds, whose inbox | System Owner
11 | Any conditions carry a named owner and a date | Chair
12 | Re-authorization triggers stated | Chair
Criteria met
Outstanding, and blocking
Gate decision: approve / approve with conditions / remediate / escalate / reject
Decision, decided by, and date

## G4
G4 — Material change
Entry criteria, expanded into what each one means in practice.
Set Status to Met, Not met or Not applicable. A completed checklist is not evidence — the evidence is the record it told you to complete.
# | Criterion | Usual owner | Status | Evidence — where the record lives | Date | Note
1 | Change described in the terms the authorized configuration uses | System Owner
2 | Dimensions touched identified before the assurance scope is chosen | Risk Lead
3 | Classified against the change-type table, with reasoning rather than a label | System Owner
4 | Autonomy change answered explicitly — any increase is never cosmetic | System Owner
5 | Second person confirms at Tier 3–4 where cosmetic or minor is claimed | Risk Lead
6 | Delta assurance scope states what is re-run and what is not, with reasons | System Owner
7 | Risk score updated where any dimension is touched | Risk Lead
8 | Post-change tier determined, and approval routed to that tier's authority | AI Governance Lead
9 | Supplier-initiated changes recorded as changes even when nothing local moved | System Owner
10 | Rollback plan stated, with how long it takes | System Owner
11 | Authorized configuration updated on completion | Architect
Criteria met
Outstanding, and blocking
Gate decision: approve / approve with conditions / remediate / escalate / reject
Decision, decided by, and date

## G5
G5 — Retirement
Entry criteria, expanded into what each one means in practice.
Set Status to Met, Not met or Not applicable. A completed checklist is not evidence — the evidence is the record it told you to complete.
# | Criterion | Usual owner | Status | Evidence — where the record lives | Date | Note
1 | Retention or deletion confirmed against the schedule, including derived stores | Data Owner
2 | Access revoked, including machine identities | Security Architect
3 | Downstream consumers identified from telemetry, not only from documentation | Architect
4 | Evidence archived and retrievable — one retrieval actually tested | System Owner
5 | Ability to explain historical decisions preserved for the liability window | Risk Lead
6 | Model weights, prompts and configurations disposed of or archived deliberately | System Owner
7 | Knowledge preservation note recorded, including what would be done differently | System Owner
8 | Residual regulatory or contractual obligations identified and owned | Risk Lead
Criteria met
Outstanding, and blocking
Gate decision: approve / approve with conditions / remediate / escalate / reject
Decision, decided by, and date

## Read me
IRGF — how to use this workbook
Part of the IRGF Practical Guide · irgframework.org
The five gate checklists from the IRGF Practical Guide, as a working workbook.
One sheet per gate, plus a summary that counts the status columns.
Two habits make these worth running:
Fill them before the meeting. The gate is the decision, not the evidence hunt.
Resist extending them after every incident. Checklists grow monotonically unless someone owns removal, and a checklist nobody finishes is worse than a short one everybody does.
Status
IRGF has not been deployed in a real organization. Thresholds, cadences and scoring anchors are reasoned defaults, not calibrated ones. Adjust them against your own incident data.